## Sheet1
Current Week | 3
LEGEND | Mobilization | Site Clearance | Earthworks | Storm Drainage | Foundations | Ground Floor Slab | Superstructure | Roof Works | Finishes
KEY | Planned Bar | Progress | Today Line
Row Number | Work Structure Code | Activity Description | Predecessor | Responsible Party | Start Week | Duration | End Week | % Complete | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
1.0 PROJECT MOBILIZATION
1 | 1 | Site Handover & Possession |  | Employer | 1 | 1 | 1 | 100
2 | 1.1 | Contractor Mobilization | 1 | Main Contractor | 2 | 2 | 3 | 100
3 | 1.2 | Establish Site Office | 2 | Main Contractor | 2 | 2 | 3 | 100
4 | 1.3 | Erect Site Hoarding & Fencing | 2 | Main Contractor | 2 | 1 | 2 | 100
5 | 1.4 | Site Safety Introduction | 3 | HSE Officer | 4 | 1 | 4 | 100
2.0 SITE CLEARANCE & DEMOLITION
6 | 2 | Vegetation Clearance & Grubbing | 5 | Main Contractor | 5 | 3 | 7 | 100
7 | 2.1 | Demolition of Existing Structures | 5 | Demolition Sub | 5 | 4 | 8 | 75
8 | 2.2 | Removal of Demolition Debris | 6 | Main Contractor | 8 | 2 | 9
9 | 2.3 | Topsoil Strip & Stockpile | 6 | Main Contractor | 8 | 2 | 9
3.0 EARTHWORKS & SUBGRADE PREPARATION
10 | 3 | Bulk Excavation - Cut to Fill | 9 | Earthworks Sub | 10 | 4 | 13
11 | 3.1 | Fill & Compaction - Embankment | 10 | Earthworks Sub | 10 | 3 | 12
12 | 3.2 | Proof Roll & CBR Testing | 11 | Engineer/Lab | 13 | 1 | 13
13 | 3.3 | Subgrade Trimming & Final Shaping | 12 | Engineer/Lab | 14 | 1 | 14
14 | 3.4 | Geotextile Installation | 13 | Main Contractor | 15 | 1 | 15
4.0 STORM DRAINAGE & SERVICES
15 | 4.1 | Setting Out Drainage Lines | 9 | Surveyor | 10 | 1 | 10
16 | 4.2 | Excavation of Drainage Trenches | 15 | Drainage Sub | 11 | 3 | 13
17 | 4.3 | Lay Storm Drainage Pipes | 16 | Drainage Sub | 14 | 4 | 17
18 | 4.4 | Construct Manholes & Inlet Chambers | 17 | Drainage Sub | 17 | 3 | 19
19 | 4.5 | Backfill & Compact Drainage Trenches | 18 | Main Contractor | 20 | 2 | 21
20 | 4.6 | CCTV Inspection & Pressure Testing | 19 | Drainage Sub | 22 | 1 | 22
21 | 4.7 | Utility Diversions - Water & Electrical | 9 | Utility Companies | 10 | 5 | 14
5.0 FOUNDATIONS
22 | 5.1 | Setting Out Building Grid Lines | 14 | Surveyor | 16 | 1 | 16
23 | 5.2 | Excavation for Foundations | 22 | Main Contractor | 17 | 2 | 18
24 | 5.3 | Blinding Concrete | 23 | Main Contractor | 19 | 1 | 19
25 | 5.4 | Foundation Reinforcement Fixing | 24 | Steel Fixer Sub | 20 | 2 | 21
26 | 5.5 | Foundation Formwork | 25 | Formwork Sub | 20 | 1 | 20
27 | 5.6 | Pour Foundation Concrete | 26 | Concrete Sub | 21 | 1 | 21
28 | 5.7 | Foundation Concrete Curing | 27 | Main Contractor | 22 | 1 | 22
29 | 5.8 | Waterproofing of Foundation | 28 | Waterproofing Sub | 23 | 1 | 23
6.0 GROUND FLOOR SLAB
30 | 6.1 | Hardcore Fill & Compaction Below Slab | 29 | Main Contractor | 24 | 1 | 24
31 | 6.2 | DPM & Insulation Layer | 30 | Main Contractor | 25 | 1 | 25
32 | 6.3 | Ground Floor Slab Reinforcement | 31 | Steel Fixer Sub | 25 | 1 | 25
33 | 6.4 | Cast In-Situ Ground Floor Slab | 32 | Concrete Sub | 26 | 1 | 26
34 | 6.5 | Slab Curing & Protection | 33 | Main Contractor | 27 | 1 | 27
7.0 SUPERSTRUCTURE
35 | 7.1 | Columns Level 1 - Reinforcement & Formwork | 34 | Steel Fixer Sub | 28 | 2 | 29
36 | 7.2 | Columns Level 1 - Concrete Pour | 35 | Concrete Sub | 30 | 1 | 30
37 | 7.3 | Suspended Slab Level 1 - Formwork | 36 | Formwork Sub | 31 | 2 | 32
38 | 7.4 | Suspended Slab Level 1 - Reinforcement | 37 | Steel Fixer Sub | 31 | 2 | 32
39 | 7.5 | Suspended Slab Level 1 - Concrete Pour | 38 | Concrete Sub | 33 | 1 | 33
40 | 7.6 | Masonry Blockwork Level 1 Walls | 39 | Masonry Sub | 34 | 3 | 36
41 | 7.7 | Columns Level 2 - Reinforcement & Formwork | 39 | Steel Fixer Sub | 34 | 2 | 35
42 | 7.8 | Columns Level 2 - Concrete Pour | 41 | Concrete Sub | 36 | 1 | 36
43 | 7.9 | Suspended Slab Level 2 - Formwork | 42 | Formwork Sub | 37 | 2 | 38
44 | 7.1 | Suspended Slab Level 2 - Reinforcement | 43 | Steel Fixer Sub | 37 | 2 | 38
45 | 7.11 | Suspended Slab Level 2 - Concrete Pour | 44 | Concrete Sub | 39 | 1 | 39
8.0 ROOF WORKS
46 | 8.1 | Roof Slab Construction | 45 | Concrete Sub | 40 | 2 | 41
47 | 8.2 | Roof Screed & Falls | 46 | Main Contractor | 42 | 1 | 42
48 | 8.3 | Waterproof Membrane Installation | 47 | Waterproofing Sub | 43 | 2 | 44
49 | 8.4 | Roof Insulation & Capping | 48 | Main Contractor | 45 | 1 | 45
50 | 8.5 | Rainwater Outlets & Parapet Flashing | 49 | Plumbing Sub | 46 | 1 | 46
9.0 FINISHES
51 | 9.1 | Internal Plastering & Screeding | 40 | Plastering Sub | 37 | 4 | 40
52 | 9.2 | Electrical First Fix | 40 | Electrical Sub | 37 | 3 | 39
53 | 9.3 | Plumbing First Fix | 40 | Plumbing Sub | 37 | 3 | 39
54 | 9.4 | External Rendering & Cladding | 40 | Main Contractor | 38 | 4 | 41